## Report
I.Current Task
No | Task Name | Pic | Plan |  |  | Actual |  |  | Complete |  | Note
|  |  | Start Date | End Date | Effort(hr) | Start Date | End Date | Effort(hr) | Today | Yesterday
1 | Why do we need Q&A? - Problems of understanding - Want for knowledge, must be ask | Thư | 2019-01-07 | 2019-01-07 | 3
2 | How to make Q&A effectively? - Identify the issue: unclear, get for more information, etc. - Check in all documents that customer supplied to make sure your question has not solved | Hiếu | 2019-01-07 | 2019-01-07 | 3
3 | How to make Q&A effectively? - With technical question, check your team /group/company or ask “Google” to solve it before asking out - Give the cross-reference clearly, completely | Phát | 2019-01-07 | 2019-01-07 | 3
4 | How to make Q&A effectively? - Attach sample screen, demo, give your suggestions if any - Convert questions to Y/N or multiple-choice types if possible | Nhật | 2019-01-07 | 2019-01-07 | 3
5 | How to make Q&A effectively? -In Q&A, give deadline that you want to receive the answer. It there is no answer until the deadline, what is impact? -Take the receiver to re-read the question before sending | Trang | 2019-01-07 | 2019-01-07 | 3
6 | Q&A focus: - Question for idea conveyed by words like: maybe, generally, etc. - What is the TBDs - Ask PL to remove all TBDs before handling to you for designing or coding | Trí Nguyễn | 2019-01-07 | 2019-01-07 | 3
7 | Q&A focus: - Conflict between requirements. Read the requirement matrix - Don’t make assumptions, just ask your PM, PL or BA | Trí Phạm | 2019-01-07 | 2019-01-07 | 3
8 | Follow up the Q&A - Track the discussion history for easier following up - If your question has not been replied or impacts to your task must be report to your PM, BA, or TL immediately - Keep in mind your manager/customer are very busy. So it is necessary to remind them about your pending issues daily, weekly. If not, your task will be impacted | Tiến | 2019-01-07 | 2019-01-07 | 3
9 | Template on Q&A Management Sheet - QMS\Document\Fsoft\Software\Template\Template_QA Management Sheet.xls | Sơn | 2019-01-07 | 2019-01-07 | 3
10
II. Next task
No | Task Name | Pic | Plan |  |  | Actual |  |  | Complete |  | Note
|  |  | Start Date | End Date | Effort(hr) | Start Date | End Date | Effort(hr) | Today | Yesterday
1 | Học SQL trên sololearn |  | 2018-01-24 | 2018-01-24 | 4
3 | Học JS |  | 2018-01-24 | 2018-01-25 | 6
III. Issue
No | Task Name | Pic | Plan |  |  | Actual |  |  | Complete |  | Solution
|  |  | Start Date | End Date | Effort(hr) | Start Date | End Date | Effort(hr) | Today | Yesterday
1 | Đứa bên cạnh hôi nách quá |  | 2018-01-23 | …
Note on C3: Dinh Vu Quoc Trung (CTC.TODHCM): các bạn đã làm gì ví dụ: Học SPD
Note on D3: Dinh Vu Quoc Trung (CTC.TODHCM): Người làm task
Note on E3: Dinh Vu Quoc Trung (CTC.TODHCM): Plan thực hiện của task
Note on H3: Dinh Vu Quoc Trung (CTC.TODHCM): Thời gian thực tế
Note on E4: Dinh Vu Quoc Trung (CTC.TODHCM): Startdate: ngày bắt đầu làm task
Note on F4: Dinh Vu Quoc Trung (CTC.TODHCM): Ngày task cần kết thúc
Note on G4: Dinh Vu Quoc Trung (CTC.TODHCM): Thời gian cần để hoàn thành task Ví dụ: 3 tiếng
Note on K4: Dinh Vu Quoc Trung (CTC.TODHCM): Tiến độ % của task ngày hôm nay
Note on L4: Dinh Vu Quoc Trung (CTC.TODHCM): Bạn đã hoàn thành bao nhiêu % công việc vào của task này vào ngày hôm qua
Note on M5: Dinh Vu Quoc Trung (CTC.TODHCM): Giải thích task - Các item của task - Đã hoàn thành những cái gì - Có khó khăn gì?
Note on B17: Dinh Vu Quoc Trung (CTC.TODHCM): Liệt kê task của ngày hôm sau
Note on B24: Dinh Vu Quoc Trung (CTC.TODHCM): Những khó khăn đang gặp phải
Note on M26: Dinh Vu Quoc Trung (CTC.TODHCM): Solution của bạn để giải quyêt vấn dề